## Sheet1
Weeks 3-8: Project-Based Learning
Number of Sprints for each Team (Batch) |  |  |  | 3
Duration of each Sprint in days |  |  |  | 10
Team Assignments
Batch # |  | Team Name |  | Team Project |  | Assigned Mentor (Trainer)
1 |  | Alpha |  | Phone Book API |  | TBD
2 |  | Beta |  | Anonymous Feedback API |  | TBD
3 |  | Gamma |  | Motivational Quotes API |  | TBD
4 |  | Delta |  | E-Sports Info API |  | TBD
Sprint 1: Weeks 3-4: For Each Team (Batch)
Week Number | Date | Objectives | Task/Project | Assigned Mentor | Q/A Mentor | Notes
Week 3 | Day 1 | 1. Backlog Refinement 2. Sprint Planning 3. Scrum (End of the Day) 4. Create a new project using existing template | As covered in the training, show them how to create an empty runable project. (Java/C#) | TBD | TBD
Week 3 | Days 2-5 | 1. Backend Work Get/Create Operation 2. Dummy Data for testing 3. Test using Postman 4. Daily Scrum Meetings (Daily EOD) | Different for each listed team project | TBD | TBD
Week 4 | Days 1-4 | 1. Persisting data in file(s) 2. Test using Postman 3. Daily Scrum Meetings (Daily EOD) | Different for each listed team project | TBD | TBD | Put this in the roadmap "Data is persisted in a Database like MySQL and this is done for data abstraction, consistency, backup and recovery. ORM is used to facilitate DB operations in Java/C#"
Week 4 | Day 5 | 1. Prepare for Sprint Review 2. Sprint Review Meeting (Demo of API) 3. Sprint Retrospective | Different for each listed team project | TBD | TBD
Sprint 2: Weeks 5-6: For Each Team (Batch)
Week Number | Date | Objectives | Task/Project | Assigned Mentor | Q/A Mentor | Notes
Week 5 | Day 1 | 1. Backlog Refinement 2. Sprint Planning 3. Add another feature in the API 4. Scrum (End of the Day) | Different for each listed team project like sorting and returning phone records in alphabetic order, filtering out unneeded text etc .. | TBD | TBD | Put this in the roadmap "Explore bootstrap templates and modify index.html of an existing template"
Week 5 | Days 2-5 | 1. [Continue] Add another feature in the API 2. Daily Scrum | Different for each listed team project | TBD | TBD
Week 6 | Days 1-4 | 1. [Continue] Add another feature in the API. 2. Daily Scrum | Different for each listed team project | TBD | TBD | Put this in the roadmap "Add CRUD Forms and make it functional using Javascript."
Week 6 | Day 5 | 1. Prepare for Sprint Review 2. Sprint Review Meeting (Demo of complete API) 3. Sprint Retrospective | Different for each listed team project | TBD | TBD
Sprint 3: Weeks 7-8: For Each Team (Batch)
Week Number | Date | Learning Objectives | Task/Project | Assigned Mentor | Q/A Mentor | Notes
Week 7 | Day 1 | 1. Backlog Refinement 2. Sprint Planning 3. Identify Bugs in the application 4. Take real life Mock Interviews 5. Scrum (End of the Day) | Different for each listed team project | TBD | TBD
Week 7 | Days 2-5 | 1. Test all functionalities and fix bugs 2. Create an artifact and run it on another machine. 3. Take real life Mock Interviews 4. Daily Scrum | Different for each listed team project | TBD | TBD
Week 8 | Days 1-4 | 1. Test the application. 2. Daily Scrum 3. Sprint Review Meeting (Demo of the entire Application) 4. Sprint Retrospective | Different for each listed team project | TBD | TBD | Put this in the roadmap "Install a Web Server on the host and deploy the application on that host"
Week 8 | Day 5 | 1. Discuss the roadmap. Show the things that are covered and a lot of things that should be explored later. 2. Take real life Mock Interviews and share the interview peparation guideline. 3. Share the progress of each team and interview feedback. | Different for each listed team project | TBD | TBD